# Travel Itinerary App - Development Roadmap v2

## Overview

Product: Collaborative AI travel planning tool First Destination: Iceland Platform: Web only (responsive) Timeline: 22-24 weeks

## Key Decisions Summary

| Decision | Choice |
| --- | --- |
| Architecture | Hybrid (pre-generated bases + AI customization) |
| Collaboration | Full: inline comments, threading, real-time sync |
| Versioning | Linear with cherry-pick feature |
| Conflicts | Detect and block until users resolve |
| Tour booking | Suggestions only (no booking integration) |
| Pricing | Free (3 regens) → Trip Pass ($8) → Unlimited ($29/yr) |
| Notifications | Email only on invites + regeneration complete |

## Phase Overview

PHASE 1: Foundation                    Week 1-3

PHASE 2: Tier 3 Data Curation          Week 2-5 (parallel)

PHASE 3: Trip Input + Generation       Week 4-7

PHASE 4: Itinerary Display             Week 8-10

PHASE 5: Collaboration                 Week 11-14

PHASE 6: AI Refinement + Versions      Week 15-18

PHASE 7: Payments + Polish             Week 19-22

PHASE 8: Testing + Launch              Week 23-24

## Phase 1: Foundation (Week 1-3)

### Goals

- Project setup and infrastructure

- Database schema deployed

- Auth working

- Basic UI shell

### Week 1: Project Setup

- Initialize Next.js 14 with TypeScript, Tailwind

- Set up Supabase project

- Configure Supabase Auth (email + Google)

- Deploy to Vercel

- Set up environment variables

### Week 2: Database + Auth

- Create all database tables (see Architecture doc)

- Set up Row Level Security policies

- Build login/signup pages

- Implement auth flow with protected routes

### Week 3: Design System

- Install and configure shadcn/ui

- Create color palette and typography

- Build layout components (header, footer, page shells)

- Create loading and error states

### Deliverables

- [ ] App deployed at yourapp.vercel.app

- [ ] Users can sign up and log in

- [ ] Database tables created with RLS

- [ ] Design system ready

## Phase 2: Tier 3 Data Curation (Week 2-5, Parallel)

This runs alongside development work. Budget 40-45 hours.

### Week 2-3: Destination Config + Routes

- Define Iceland anchors (10-15) with seasonality

- Map out regions (7-8) with typical days

- Set pacing rules for each level

- Document 45-50 route segments

- Research cell coverage, gas stations, hazards

### Week 4-5: Spots + Activities + Labels

- Identify 35-40 hero spots

- Write pro tips, skip-if conditions, photo spots

- List 25-30 bookable activities

- Add operator recommendations with reasoning

- Create labels for all spots and activities

- Define "similar if less physical" / "similar if more adventure" mappings

### Deliverables

- [ ] destinations/iceland/config.json

- [ ] destinations/iceland/routes.json

- [ ] destinations/iceland/spots.json

- [ ] destinations/iceland/activities.json

- [ ] All data loaded into Supabase

## Phase 3: Trip Input + Generation (Week 4-7)

### Goals

- Complete trip creation form

- Hybrid generation working

- Similar itinerary matching

- Base itineraries generated

### Week 4-5: Trip Form

- Destination selector (Iceland only)

- Date picker with validation

- Block impossible combos (northern lights in summer)

- Warn on suboptimal combos

- Travelers selector

- Pacing toggle

- Anchors multi-select (max 3)

- Budget tier (optional)

- Save trip to database

### Week 6: Similar Matching + Base Generation

- Generate ~225 base itineraries for Iceland

- Build similarity matching algorithm

- "Find similar itineraries" feature

- Allow users to start from similar

### Week 7: Hybrid Generation

- Implement hybrid generation flow

- AI uses closest base as reference

- Generate custom for user's anchors

- Cache generated itineraries

- Personalize dates on cached itineraries

### Deliverables

- [ ] Trip creation form complete

- [ ] 225 base itineraries generated and cached

- [ ] Similar matching working

- [ ] Hybrid generation working

- [ ] User can generate initial itinerary

## Phase 4: Itinerary Display (Week 8-10)

### Goals

- Beautiful itinerary view

- Interactive map

- Day-by-day display

- Supporting tabs

### Week 8: Core Itinerary View

- Trip overview header

- Trip stats summary

- Anchors covered section

- Day navigation (tabs or scroll)

- Day cards with summary

### Week 9: Expanded Day View

- Timeline with times

- Spot cards with images, descriptions

- Drive segments with logistics

- Meal suggestions

- Accommodation options

- Labels display

### Week 10: Map + Supporting Features

- Mapbox integration

- Route polylines

- Day-colored markers

- Click marker → scroll to spot

- Prepare tab (packing list, practical info)

- Budget estimate tab

### Deliverables

- [ ] Full itinerary view working

- [ ] Interactive map with routes

- [ ] Day expansion working

- [ ] Supporting tabs complete

## Phase 5: Collaboration (Week 11-14)

### Goals

- Invite collaborators

- Real-time comments

- Inline text selection comments

- Presence indicators

### Week 11: Collaborator Management

- Invite by email flow

- Email invitation template (Resend)

- Accept/decline invitation

- Role management (owner, editor, commenter, viewer)

- Collaborator list in UI

### Week 12: Comments - Basic

- Add comment to any item (day, spot, drive)

- Comment list/sidebar

- Threading (reply to comments)

- Delete comment

- Real-time sync for comments

### Week 13: Comments - Inline

- Select text to comment (Google Docs style)

- Highlight text with comments

- Show comment on highlight click

- Store selection coordinates

### Week 14: Presence + Polish

- Show who's viewing (avatars)

- Real-time presence updates

- Comment notifications (in-app)

- Collaboration UI polish

### Deliverables

- [ ] Invite flow working with email

- [ ] Comments with threading

- [ ] Inline text selection comments

- [ ] Real-time sync for all collaboration

- [ ] Presence indicators

## Phase 6: AI Refinement + Versions (Week 15-18)

### Goals

- Comment classification

- Conflict detection

- AI regeneration

- Version history with cherry-pick

### Week 15: Comment Classification

- Client-side pre-classification (patterns)

- AI classification for complex comments

- Intent display on comments

- Classification confidence

### Week 16: Conflict Detection + Regeneration Prep

- Detect conflicts between comments

- Block regeneration if conflicts

- Show conflict UI

- "Pending comments" summary before regenerate

- Regeneration button with remaining count

### Week 17: AI Regeneration

- Build regeneration pipeline

- Tiered AI (rules → Haiku → Sonnet)

- Context compression

- Apply modifications

- Create new version

- Regeneration complete email

### Week 18: Versions + Cherry-Pick

- Version history list

- Compare versions (diff view)

- Cherry-pick UI (select best of each day)

- Create version from cherry-pick

- Revert to previous version

### Deliverables

- [ ] Comments classified with intent

- [ ] Conflicts detected and blocked

- [ ] Regeneration working

- [ ] Version history with diff

- [ ] Cherry-pick working

## Phase 7: Payments + Polish (Week 19-22)

### Goals

- Stripe integration

- Paywall flow

- PDF export

- Trip lifecycle

### Week 19: Paywall + Stripe

- Stripe integration

- Trip Pass ($8) purchase flow

- Unlimited ($29/yr) subscription

- Paywall at 3 regenerations

- Payment success handling

### Week 20: Exports + Sharing

- Basic PDF export (template)

- Share link generation

- Public view for shared trips

- Duplicate trip feature

### Week 21: Trip Lifecycle

- Completed trip status (after end date)

- View-only mode for completed

- Post-trip feedback prompt

- Trip archive/delete

### Week 22: Polish + Performance

- Loading states everywhere

- Error handling throughout

- Performance optimization

- Mobile responsive polish

- Accessibility review

### Deliverables

- [ ] Payments working

- [ ] Paywall flow complete

- [ ] PDF export working

- [ ] Share links working

- [ ] Trip lifecycle complete

- [ ] Polish pass done

## Phase 8: Testing + Launch (Week 23-24)

### Week 23: Testing

- End-to-end testing (real scenarios)

- Test with 10-15 beta users

- Bug fixes from testing

- Edge case handling

- Cost monitoring setup

### Week 24: Launch

- Analytics setup (PostHog)

- Error monitoring (Sentry)

- Landing page polish

- Documentation

- Soft launch

- Gather feedback

### Deliverables

- [ ] Beta tested

- [ ] Analytics working

- [ ] Error monitoring working

- [ ] Launched!

## Parallel Work Summary

| Primary | Parallel |
| --- | --- |
| Week 1-3: Foundation | Week 2-5: Tier 3 Data |
| Week 8-10: Display | Week 11: Start Collaboration |

## Risk Mitigation

| Risk | Mitigation |
| --- | --- |
| AI regeneration quality poor | Start Week 15 work early, iterate on prompts |
| Real-time sync complex | Use Supabase Realtime, proven patterns |
| Tier 3 data takes too long | Start early, parallelize, prioritize core data |
| Costs higher than expected | Implement all cost controls from start |
| Low conversion at paywall | Test pricing with beta users, adjust |

## Success Metrics (Launch +30 days)

Usage:

- 100+ trips created

- 60%+ form completion rate

- 20%+ trips shared with collaborators

Quality:

- Avg regenerations per trip: 2-4

- Conflict rate < 10% of regenerations

- User satisfaction > 4/5

Business:

- 40%+ paywall conversion

- < $0.50 avg cost per trip

- 10+ paying customers

## Post-Launch (V2.1+)

After launch, prioritize based on user feedback:

- Calendar sync export

- More destinations

- @mentions in comments

- Dietary filtering

- Weather contingency plans

- Mobile app

## Weekly Milestones Checklist

### Foundation

- [ ] Week 1: Project deployed, Supabase connected

- [ ] Week 2: Auth working, database ready

- [ ] Week 3: Design system complete

### Data

- [ ] Week 3: Iceland config + routes done

- [ ] Week 5: All Tier 3 data complete and loaded

### Core Features

- [ ] Week 5: Trip form complete

- [ ] Week 7: Generation working

- [ ] Week 10: Itinerary display complete

- [ ] Week 14: Collaboration complete

- [ ] Week 18: AI refinement + versions complete

### Launch Prep

- [ ] Week 22: Payments + polish complete

- [ ] Week 24: Launched!